## PROJECT OUTLINE URL
https://github.com/cmpietro/PROJECT-2-Visualize-Me-Captain/projects

## MEETING NOTES
MEETING NOTES:
STARTING DOCUMENTATION - 8-28-19
MEETING NOTES: 8-29-19 Discussion all on Git hub - Zoom touchbase
8-30-19: Zoom meeting short - Agreed to continue working on focus of finding datasets
UPDATE FROM 8-31-19 MEETING: Enzo having fun with JSON data and working with the FBI data set, has set deadline to complete task the hard way before doing the easy way. Ian is email site again regarding API key as well as starting to examine the mass shooting data. Carol will be working on the CDC data and Beth is continuing her work discussed on Friday night, Beth's was absent from this meeting. UPDATE from Friday, 8-30-19: Beth, Enzo and Carol met and discussed plan for the beginning structure, outline of goals and discussion of data sets. All agreed on starting approach. Ian working and couldn't make Friday call.
9/1/19 Regarding project. For Wednesday: I would like to have at LEAST four definitive datasets determined okay for use, Mapping out of site / application. My thoughts are: Title, summary explanation of how to use data / data set. BIG map of US, with drop downs for various views, side selection for overlays of related data. Then below map, static views of the same data, graphed in more traditional ways, explaining how we used the data ... then a summary paragraph below that explaining our views / thoughts and how we created the mappingI think bootstrap would work FINE: TITLE: then centered 1/4 page intro, then whole block for mapping, then 1/4 each for the static views, then 1/4 page centered summary with possibly two 1/8 sides?
SUMMARY OF MEETING: 9-3-19 1. discussion of focus of study, need to keep exploring but also focus on what story we CAN tell in the time given. 2. Enzo working on getting JSON data for all 50 states from the FBI data, however, would mean 150 potential API calls, we agreed that it would be better to pull data upfront and place in Database rather than make live API calls for that much data. We can use the potential "bonus" news pulls for the API call requirement (for live data) 3. Beth discussed questions she had about guns and gun types - Carol and Enzoy attempted to assist in Beth's understanding (basically the choices for mass shootings oft comes to marketing and perceptions as well as toxic masculinity 4. We also discussed the clear disparities in numbers, more people of color are killed by guns but gun ownership rates by people of color are dramatically lower than ownership rates of whites. 5. we discussed how to include mental health statistics in the research and see what that shows too. 6. We did not get an update from ian and the update from Enzo was cut slightly short by the "free" version cut off timing. 7. Carol will create a pencil drawing for tomorrows class and Enzo will push up to Git at least one states FBI data for review tonight.
MEETING 9-4-19 MEETING TODAY: after class. Review of story board, Review of great idea by Beth, potential decision to hold due to requirements being met. we reviewed thoughts on DATES; deciding to determine date ranges of visualization after we have all data sets determined and the MIN and MAX of the date ranges. Thank you each for your contributions. Talk to you Tomorrow at 8 pm
9-5-19 - THANK YOU to Beth and Enzo for the good discussion. TODAY's meeting: Discussion again of date ranges and making a determination on that, once all data sets are secured and evaluated. NO MEETING Friday, we WILL meet Saturday in Class for full discussion. Please slack out any exciting discoveries (or boring ones). Additionally we discussed types of guns and reviewed some of the data already on GITHUB. Beth asked questions about what defines certain types of guns as automatic, semi auto etc... we discussed why one category "Machine gun" had so many guns (it includes semi auto). We also discussed a show Beth listened too -- Daily show --- on NPR from a Times reporter who is also asking questions of Banks and how they are responsible for enabling purchase of the weapons and ammunition used in mass shootings. Enzo said his knew people at Key who also were using behavior studies to track these types of purchases, similar to money laundering.. Enzo reviewed the mass shooting database, he knew of and we decided to use the Mother Jones data as it has a bigger date range.
9-6-19 notes from tom: 1, establish visualization transition. 2. scraping five headlines were received as a good idea. 3. we need to decide on which features are absolute/finalized for monday. 4. which then contributes to the flow chart. think through process (click on graphic, goes to flask with route of specific data [from various data sources]). 5. heat map is the interactive visualization, and four static visuals // plotly gun violence views // (all proposed visuals need finalized by monday). 6. have a sudo code for everything in the flow chart. 7. data transition: in hold because of FBI/UCR data. 8. by next saturday to setup in Heroku. 9. update frequency, hourly, daily? how does this appear in the flow chart reflecting update frequency? 11: various discussion on why Enzo's data is getting throttled. save data as you go. import time, time.sleep(seconds)
9-8-19 NOTES: Carol shared data plan, pseudo scripting, requirements. BETH: working on homework and working on … IAN: stuck on API key. Enzo: to work with Ian on API key and work on database and getting data to main git Beth: taking on building the building of the base map Carol: To finish off the HTML Enzo reported that an Ancillary meeting was held with planning on database work.
9-9-19 NOTES IN CLASS: Discovery that Ian's data API will not work for our purposes. Worked with Tom to get ideas. Enzo's data needed to be repulled -- discovery of data issues. New data holds promise and will be distributed as soon as possible.
9-11-19 CLASS HI - Thank you all for the good working session last night. FYI: I have taken copies from the master for the html / css etc... and will work with them locally and push to my branch. Any updates can then be reconciled on Saturday / Monday prior to final launch. I am currently working on the news portion as well as a static visualization or two - while Beth is working on the map / layers with Enzo working on data storage. I'm no longer working as of NOW... So you have my full attention until launch day. I'm going to work on an outline as a conversation for the 10 min presentation for myself - let me know if you want me to share.
9-12-19 - Thank you for the meeting. Today's conversation: Enzo gave an update on mongo versus sql and difficulties of cleaning data. The ideal would be to not have two different datasets, to go with either database. We would prefer ONE database, especially since time is an issue. Enzo will most likely be dropping SQL and using Mongo. We viewed some of the data and discussed some of the differences between SQL and nonSQL databases. Enzo stated he felt more comfortable now. Beth checked in via slack and will be working on coding and provide an update tomorrow. Ian is working on building a layer without data - and - will pull down the latest GIT version of the JS to play around with what he can .... Carol demo'd some of the Static views being added to the web site and discussed views about the application. The paragraphs from each of us, needs to be like bookends to a pop-up version of a story, that uses the data to give our version of the story. We agreed that the better the visuals the easier the presentation would be. We agreed - that we would meet tomorrow, but that everyone did not need to be there. Ian has double work on Friday, but would work on his portion Saturday. etc... Thank you all for your work and participation in the project.

## MEETING PLAN
PLAN FOR MEETING
DAILY MEETINGS on ZOOM - 8pm - 8:30 pm
IF we are not able to meet - slack out any developments
summary of all meetings to be slacked out that day
NEXT MEETING DATE 9-7-19

## SUMMARY 8-28-19
GROUP – 1
VISUALIZE ME!
We live in a violent world and gun violence is one of the more dramatic expressions. We found several potential data sets for visualizations. Starting with our inspiration: https://fivethirtyeight.com/features/gun-deaths/. This interactive graphic is a part of a project that explored the more than 33,000 annual gun deaths in the US and what is would take to bring that number down. We also have requested an API key for a dataset of gun ownership, https://www.gunpolicy.org/api. There is also the FBI, which has data sets available on crime data https://crime-data-explorer.fr.cloud.gov/explorer/national/united-states/crime. There is also the CDC, which is the core data set used in the 538.com site, where we could explore other at-risk behaviors.
We would like to create a view into gun violence by looking under-the-hood, so to speak of several data-sets and views of the various aspects that create the topic of “Gun Violence”. Some topics to explore: Gun Death; type of death, suicide, homicide, accident, Gun Ownership; lack of data, location of owner, any relationship of ownership to death, Gun Crime: use of a gun in a crime, location of crimes, Escalation of violence; mass shootings, are just a few.
We would like to create interactive map visualizations with overlays representing the story of the data we find. Additionally, we would like to create some additional view-points, focusing on the many side views of the broad topic of gun violence. We have researched additional JS libraries and would like to use TEECHART for creation of some of the graphics or Angular.js for developing the application. We need additional time to explore these options before deciding. We have decided to use SQL, specifically postgres for storing the data.

## TEAM
GROUP 1
NAME | EMAIL | NUMBER | GIT HUB | ROLE | ADDITIONAL TASKS
Beth Grace |  | 216- 544-7719 | BGrace3
Ian Valentik |  | 440-668-8691 | IvIntk
Enzo Adriano |  |  | crescenzo77
Carol Pietro | carol.m.pietro@gmail.com | 216-538-0287 | cmpietro

## Requirements
1 | YOUR Data must tell the story
2 | Interactive Data
3 | Must have a 10 minute presentation, approach, data munging and visualization
4 | FLASK api / restful api, html / css / javascript / and a database
5 | Creative d3 - non-standard
combination of web scraping and leaflet and /or plotly
a dashboard page with multiple charts that update from the same data
or a THICK server - live time ETL - performs multiple manipulations on data in a database prior to visualization
would include at least ONE library that we did not cover
Have to have more than 100 records
more than 1 data set
more than 20 commits
more than 3 visualizations
BONUS: Heroku / AWS / Digital Oceon
more than one API
using Geo JSON

## TRACKING
ITEM NUMBER | DESCRIPTION | TECHNOLOGY | TOPIC AREA | STATUS | LOCATION TO DETAILS
1 | Build Github and keep updated | GIT | All | Done and ongoing | NONE --
2 | Get / pull / source all data and document Data Points | Various | All
3 | Once data points are documented, BUILD Tables to hold interactive data | Postgres / SQL database | All interactive data
4 | Start sourcing SOME of the data into SQL for testing interactivity | Postgres / SQL database | All interactive data
5 | Start on BASE MAP | JavaScript | all
6 | Build layer one | JavaScript
7 | TEST LAYER ONE | TEST
8 | Build layer two | JavaScript
9 | TEST LAYER TWO | TEST
10 | Build layer three | JavaScript
11 | TEST LAYER THREE | TEST
12 | Build layer four | JavaScript
13 | TEST LAYER FOUR | TEST
14 | Add all the layers to the Base Map
15 | Add controls to the map
16 | Add legend to the map
17 | Add instructions / user guide (HERE (?) HTML)
18 | Build HTML - with MAP for testing interactivity of site so far | HTML
19 | TEST interative map and functionalilty | TEST
20 | Build static display one | INDIVIDUAL CHOICE
21 | Build static display two | INDIVIDUAL CHOICE
22 | Build static display three | INDIVIDUAL CHOICE
23 | Build static display four | INDIVIDUAL CHOICE
24 | Add Static displays to Git and Reference in HTML
25 | Test add of static displays
26 | Add Webscraper to JAVA SCRIPT --- for pulling of FOUR DAYS of news
27 | Add four display areas within HTML for the four days of news
28 | TEST web scraping | TEST
29 | TEST FULL site up to this point | TEST
30 | WRITE conclusions one
31 | WRITE conclusions two
32 | WRITE conclusions three
33 | WRITE conclusions four
34 | Add conclusions to the HTML - | HTML
35 | Validate project against Requirements
36 | HEROKU | HEROKU
37
38
39

## PIECES PARTS
ITEM NUMBER | DESCRIPTION | TECHNOLOGY | TECH TYPE | TOPIC AREA | STATUS
1 | Repository | Git | Github | All
2 | Data Storage | database | Postgres | All interactive data
3 | Interactive Web page | HTML | HTML | All topics
4 | Interactive Web page | Interactive Web page | Bootstrap
5 | Interactive Web page | Interactive Web page | Map
6 | Interactive Web page | Interactive Web page | JS
7 |  |  | CSS
8 |  |  | HEROKU
9
10

## STORY BOARD
https://carolpietro919989.invisionapp.com/board/Visualize-Me---ck05b3sfo0c7d0stms423mw2r?v=ozc%2BIKkshSKk6%2BJ8GDUZuw%3D%3D&linkshare=urlcopied

## Visualization
Large US map representing gun deaths
Overlay with Gun ownership
Potential overlay with FBI data
zoom down into the REGION
present similar data
three views
zoom down into the state

## Initial Data Plan
https://fivethirtyeight.com/features/gun-deaths/ | 1 | Gather all the potential data sets
https://data.world/datasets/guns | 2 | map out the data and determine the best "STORY" view point
| 3 | Verify the data sets selected meet the requirements of the project
| 4 | Clean the data and group into segments
| 5 | create a database and import the data
| 6 | Create the application
| 7 | Create the visualization
| 8 | test all the visualizations and make sure they work
| 9 | polish off the STORY and
| 10 | deploy the Heroku
| 1 | gather data
| 2 | Document all datasets -
| 3 | Map out Data POINTS
| 4 | document Headers of all data
| 5 | Determine HOW we are to gather the data for the application, for EACH data set
a. DOCUMENT EACH data set and how we are going to get each dataset into the appliation
| 6 | Determine what type of database will be used - (postgres versus mongo) POSTGRES most voted on
| 7 | SKETCH out application:
| 8 | BUILD the database to store the DATA - Build tables off documented datasets
| 9 | Determine IF and WHAT - STILL graphs to use --- using a library not used previously
| 10 | CODE - HTML - shell
| 12 | CODE JS - MAP - with four overlays
| 13 | CODE CSS
| 14 | ADD in the DATABASE
| 15 | TEST and retest

## Mass Shooting CSV
case | location | date | summary | fatalities | injured | total_victims | location | age_of_shooter | prior_signs_mental_health_issues | mental_health_details | weapons_obtained_legally | where_obtained | weapon_type | weapon_details | race | gender | sources | mental_health_sources | sources_additional_age | latitude | longitude | type | year
case
location
date
summary
fatalities
injured
total_victims
location
age_of_shooter
prior_signs_mental_health_issues
mental_health_details
weapons_obtained_legally
where_obtained
weapon_type
weapon_details
race
gender
sources
mental_health_sources
sources_additional_age
latitude
longitude
type
year
case | location | date | summary | fatalities | injured | total_victims | location | age_of_shooter | prior_signs_mental_health_issues | mental_health_details | weapons_obtained_legally | where_obtained | weapon_type | weapon_details | race | gender | sources | mental_health_sources | sources_additional_age | latitude | longitude | type | year
Dayton entertainment district shooting | Dayton, OH | 2019-08-04 | Connor Betts, 24, died during the attack, following a swift police response. He wore tactical gear including body armor and hearing protection, and had an ammunition device capable of holding 100 rounds. Betts had a history of threatening behavior dating back to high school, including reportedly having hit lists targeting classmates for rape and murder. | 9 | 27 | 36 | Other | 24 | - | - | Yes | - | semiautomatic rifle | AR-15-style rifle, with a 100-round capacity ammunition drum | White | M | https://www.nytimes.com/2019/08/04/us/dayton-ohio-shooting.html; https://www.nytimes.com/2019/08/04/us/mass-shootings-dayton-el-paso.html; https://www.washingtonpost.com/nation/2019/08/04/nine-fatally-shot-dayton-including-suspect-day-after-mass-shooting-texas/; https://www.washingtonpost.com/national/police-chief-it-seems-to-defy-believability-that-dayton-shooter-would-kill-his-own-sister/2019/08/05/920a895c-b79e-11e9-b3b4-2bb69e8c4e39_story.html; https://www.cnn.com/2019/08/05/us/connor-betts-dayton-shooting-profile/index.html | - | - | 39.7573 | -84.1849 | Mass | 2019
El Paso Walmart mass shooting | El Paso, TX | 2019-08-03 | Patrick Crusius, 21, who was apprehended by police, posted a so-called manifesto online shortly before the attack espousing ideas of violent white nationalism and hatred of immigrants. "This attack is a response to the Hispanic invasion of Texas," he allegedly wrote in the document. | 22 | 26 | 48 | Workplace | 21 | - | - | Yes | - | semiautomatic rifle | AK-47-style rifle, per authorities | White | M | https://www.washingtonpost.com/nation/2019/08/04/investigators-search-answers-after-gunman-kills-el-paso/; https://www.nytimes.com/2019/08/04/us/mass-shootings-dayton-el-paso.html; https://www.apnews.com/5fb2144947974631912d1efa889f932b | - | - | 31.7711 | -106.3757 | Mass | 2019
Gilroy garlic festival shooting | Gilroy, CA | 2019-07-28 | Santino William LeGan, 19, fired indiscriminately into the crowd near a concert stage at the festival. He used an AK-47-style rifle, purchased legally in Nevada three weeks earlier. After apparently pausing to reload, he fired additional multiple rounds before police shot him and then he killed himself. A witness described overhearing someone shout at LeGan, "Why are you doing this?" LeGan, who wore camouflage and tactical gear, replied: â€œBecause I'm really angry." The murdered victims included a 13-year-old girl, a man in his 20s, and six-year-old Stephen Romero. | 3 | 12 | 15 | Other | 19 | TBD | - | Yes | Nevada, on July 9 | semiautomatic rifle | AK-47-style rifle, per authorities | - | M | https://www.cbsnews.com/live-news/garlic-festival-mass-shooting-gilroy-california-victims-suspect-santino-william-legan-live-updates/; https://www.sfgate.com/news/article/Report-Suspect-ID-in-Gilroy-Garlic-Festival-14192736.php; https://www.nytimes.com/2019/07/29/us/gilroy-festival-shooting.html; https://www.latimes.com/california/story/2019-07-29/what-we-know-about-gilroy-garlic-festival-shooting-suspect-santino-william-legan; https://www.washingtonpost.com/nation/2019/07/29/multiple-people-reportedly-injured-shooting-california-food-festival/; https://heavy.com/news/2019/07/santino-william-legan/; https://www.cnn.com/2019/08/06/us/gilroy-festival-shooting/index.html | - | - | 36.9972 | -121.5848 | Mass | 2019
Virginia Beach municipal building shooting | Virginia Beach, VA | 2019-05-31 | DeWayne Craddock, 40, a municipal city worker wielding handguns, a suppressor and high-capacity magazines, killed en masse inside a Virginia Beach muncipal building late in the day on a Friday, before dying in a prolonged gun battle with police. Craddock reportedly had submitted his resignation from his job that morning. He was a veteran of the Virginia Army National Guard, and "had a shaved head, bodybuilderâ€™s physique and cameras in the windows of his house on a peaceful cul-de-sac," according to the Washington Post. | 12 | 4 | 16 | Workplace | 40 | TBD | - | Yes | - | 2 handguns | .45-caliber handguns | Black | M | https://www.washingtonpost.com/local/public-safety/virginia-beach-officials-expect-to-release-additional-details-of-mass-shooting/2019/06/02/a001b856-852f-11e9-a870-b9c411dc4312_story.html; https://pilotonline.com/news/local/virginia-beach-mass-shooting/article_e15ea290-853f-11e9-aa50-93751bba3c3b.html; https://pilotonline.com/news/local/virginia-beach-mass-shooting/article_c8353020-84a1-11e9-aa12-d3bf967368c4.html; https://www.reuters.com/article/us-virginia-shooting-guns/virginia-beach-shooter-bought-guns-he-used-legally-federal-agent-idUSKCN1T23EZ; https://www.usatoday.com/story/news/nation/2019/06/02/virginia-beach-shooter-dewayne-craddock-puzzles-law-enforcement/1319550001/ | - | - | 36.7544 | -76.0604 | Mass | 2019
Harry Pratt Co. warehouse shooting | Aurora, IL | 2019-02-15 | Gary Martin, 45, went on a rampage inside the warehouse in response to being fired from his job and died soon thereafter in a shootout with police. Among his victims were five dead coworkers and five injured police officers. Martin had a felony record and lengthy history of domestic violence; he was able to obtain a gun despite having had his Illinois firearms ownership identification card revoked. According to a report from prosecutors, Martin told a co-worker the morning of the shooting that if he was fired he was going to kill employees and police. | 5 | 6 | 11 | Workplace | 45 | Yes | (pending) | No | - | handgun | Smith & Wesson handgun, with a green sighting laser | Black | M | https://www.washingtonpost.com/nation/2019/02/16/man-kills-five-warehouse-shooting-spree-shortly-after-being-fired-illinois-police-say/?utm_term=.9863ec4ffc41; https://www.cnn.com/2019/02/17/us/aurora-shooting-termination/index.html; https://www.wsj.com/articles/companies-roll-out-gunshot-detectors-at-the-office-11550575801; https://www.cbsnews.com/news/gary-martin-aurora-illinois-plant-gunman-threatened-violence-if-fired-prosecutors-say/ | - | - | 41.7537 | -88.3311 | Mass | 2019
Pennsylvania hotel bar shooting | State College, PA | 2019-01-24 | Jordan Witmer, 21, shot three people at a Ramada Hotel bar near Penn State University, including a former girlfriend he was there with. He then fled the bar, crashed his car about a mile away, and stormed into a random house, fatally shooting an elderly resident and then himself. Witmer, who had a legal carry permit for his handgun, had just finished a three-year stint in the US Army; ten days prior to the attack he had been convicted on drunk driving-related charges in Kentucky, where he'd been stationed. | 3 | 1 | 4 | Other | 21 | - | - | Yes | - | handgun | - | White | M | http://www.wistv.com/2019/01/26/details-emerge-about-shooting-rampage-near-penn-state/; https://www.pennlive.com/news/2019/01/state-college-shooter-pleaded-guilty-to-dui-crash-charges-days-before-killings.html; https://www.pennlive.com/news/2019/01/man-who-killed-3-in-state-college-wanted-to-be-a-cop-relatives-say.html | - | - | 40.7851 | -77.8394 | Spree | 2019
SunTrust bank shooting | Sebring, FL | 2019-01-23 | Zephen A. Xaver, 21, fatally shot five women inside a bank and then called the police to confess. He was armed with a handgun and wore a bulletproof vest. He reportedly ordered the women to lie down on the floor and shot them execution-style. After a standoff with police, he surrendered and was taken into custody. A week prior, Xaver had quit a job as a prison guard trainee, and authorities said they believed the shooting was "a random act" and that roberry did not appear to be a motive. An ex-girlfriend in Indiana told local media she'd been â€œscared for yearsâ€ by Xaverâ€™s talk of violence and death, but that her warnings to others (who she did not identify) were not taken seriously. She said sheâ€™d first met Xaver in a psychiatric hospital in 2013. In March 2017, Michigan State Police documented an incident in which Xaver indicated he was â€œpossibly thinking of suicide by cop and taking hostages." | 5 | 0 | 5 | Workplace | 21 | Yes | Xaver was reported to have a lenghty history of expressing violent desires; an ex-girlfriend said she first met him at a psychiatric hospital in 2013. | Yes | - | handgun | 9 mm handgun | White | M | https://wsbt.com/news/local/classmate-says-florida-bank-shooter-who-allegedly-killed-5-attended-bremen-high-school; https://www.washingtonpost.com/nation/2019/01/23/several-people-shot-after-gunman-barricades-himself-florida-bank-authorities-say/; https://www.wptv.com/news/state/accused-bank-shooter-zephen-xaver-fascinated-with-violence-ex-girlfriend-says; https://www.npr.org/2019/01/24/688183605/man-charged-with-murder-after-allegedly-killing-5-women-at-suntrust-bank-in-flor; https://www.wesh.com/article/sebring-bank-shooting-latest/26012533; https://www.apnews.com/c3523d282b2942739240731daaf797c2 | https://wsbt.com/news/local/classmate-says-florida-bank-shooter-who-allegedly-killed-5-attended-bremen-high-school; https://www.washingtonpost.com/nation/2019/01/23/several-people-shot-after-gunman-barricades-himself-florida-bank-authorities-say/ | - | 27.471 | -81.4585 | Mass | 2019
Mercy Hospital shooting | Chicago, IL | 2018-11-19 | Juan Lopez, 32, confronted his former fiancÃ©, ER doctor Tamara O'Neal, before shooting her and opening fire on others at the hospital, including a responding police officer, Samuel Jimenez, and a pharmacy employee, Dayna Less. Lopez was fatally shot by a responding SWAT officer. Lopez had a history of domestic abuse against an ex-wife, and was kicked out of a fire department training academy for misconduct against female cadets. | 3 | 0 | 3 | Workplace | 32 | - | - | - | - | semiautomatic handgun | 9mm handgun | Latino | M | https://www.cnn.com/2018/11/19/us/mercy-hospital-chicago-shooting/index.html; https://www.chicagotribune.com/news/local/breaking/ct-met-shooting-mercy-hospital-chicago-20181119-story.html; https://6abc.com/chicago-shooting-4-dead-including-officer-gunman/4720955/; https://chicago.cbslocal.com/2018/11/19/mercy-hospital-gunman-officer-killed; https://abc7ny.com/mercy-hospital-chicago-shooting-4-dead-including-officer-gunman/4720765/; https://abc7chicago.com/mercy-hospital-gunman-what-we-know/4725117/ | - | - | 41.8477 | -87.622 | Mass | 2018
Thousand Oaks nightclub shooting | Thousand Oaks, CA | 2018-11-07 | Ian David Long, 28, dressed in black and armed with a handgun and a â€œsmoke device,â€ approached the Borderline Bar & Grill â€” a country music venue popular with college students â€” close to midnight and opened fire, killing a security guard and then others in the club, including a sheriffâ€™s deputy responding to the attack. Long was found dead at the scene from apparent suicide. He was a former Marine and had a history of interactions with local law enforcement, including a mental health evaluation in which heâ€™d been cleared. | 12 | 22 | 34 | Other | 28 | Yes | Per the LATimes: "Sheriff Geoff Dean said his department had had several interactions with Long, including a call to his home in April for a complaint of disturbing the peace. Deputies at the time said Long was irate and acting irrationally, Dean said. They called in mental health professionals to evaluate him, and they concluded he did not need to be taken into custody." | Yes | A gun store in Simi Valley | semiautomatic handgun | Glock 21, .45 caliber; high-capacity magazine | - | M | http://www.latimes.com/local/lanow/la-me-ln-thousand-oaks-20181107-story.html; https://www.washingtonpost.com/nation/2018/11/08/multiple-injuries-reported-bar-shooting-thousand-oaks-calif/; https://www.nytimes.com/2018/11/08/us/shooting-california-thousand-oaks.html; https://www.nytimes.com/2018/11/08/us/ian-david-long-california-shooter.html; https://www.wsj.com/articles/multiple-injuries-reported-in-bar-shooting-in-thousand-oaks-california-1541666907 | http://www.latimes.com/local/lanow/la-me-ln-thousand-oaks-20181107-story.html | - | 34.1769 | -118.8748 | Mass | 2018
Tree of Life synagogue shooting | Pittsburgh, PA | 2018-10-27 | Robert D. Bowers, 46, shouted anti-Semitic slurs as he opened fire inside the Tree of Life synagogue during Saturday morning worship. He was armed with an assault rifle and multiple handguns and was apprehended after a standoff with police. His social media accounts contained virulent anti-Semitic content, and references to migrant caravan "invaders" hyped by President Trump and the Republican party ahead of the 2018 midterms elections. | 11 | 6 | 17 | Religious | 46 | - | - | Yes | (Unclear; investigators confirmed he owned 10 guns in total, all purchased and possessed legally, and had a handgun license) | semiautomatic rifle; semiautomatic handguns | AR-15; Glock .357 (3) | White | M | https://www.nytimes.com/2018/10/27/us/active-shooter-pittsburgh-synagogue-shooting.html; https://www.cnn.com/us/live-news/pittsburgh-synagogue-shooting/h_0c180f52c8d032fd47eef570cc5065c2; https://www.nytimes.com/2018/10/30/us/ar15-gun-pittsburgh-shooting.html | - | - | 40.4439 | -79.9214 | Mass | 2018

## Mass Shooting URL
https://www.motherjones.com/politics/2012/12/mass-shootings-mother-jones-full-data/

## 538 mortality data.csv
| year | month | intent | police | sex | age | race | hispanic | place | education
year
month
intent
police
sex
age
race
hispanic
place
education
| year | month | intent | police | sex | age | race | hispanic | place | education
1 | 2012 | 1 | Suicide | 0 | M | 34 | Asian/Pacific Islander | 100 | Home | BA+
2 | 2012 | 1 | Suicide | 0 | F | 21 | White | 100 | Street | Some college
3 | 2012 | 1 | Suicide | 0 | M | 60 | White | 100 | Other specified | BA+
4 | 2012 | 2 | Suicide | 0 | M | 64 | White | 100 | Home | BA+
5 | 2012 | 2 | Suicide | 0 | M | 31 | White | 100 | Other specified | HS/GED
6 | 2012 | 2 | Suicide | 0 | M | 17 | Native American/Native Alaskan | 100 | Home | Less than HS
7 | 2012 | 2 | Undetermined | 0 | M | 48 | White | 100 | Home | HS/GED
8 | 2012 | 3 | Suicide | 0 | M | 41 | Native American/Native Alaskan | 100 | Home | HS/GED
9 | 2012 | 2 | Accidental | 0 | M | 50 | White | 100 | Other specified | Some college
10 | 2012 | 2 | Suicide | 0 | M | NA | Black | 998 | Home | NA
11 | 2012 | 2 | Suicide | 0 | M | 30 | White | 100 | Home | Some college

## MORTALITY URL
https://github.com/fivethirtyeight/guns-data

## FBI DATA
<div class='col-lg-7 col-md-12'> | ** NEBRASKA is missing
<div class='box'>

## GUN OWNERSHIP URL
url = "https://www.gunpolicy.org/index.php?option=com_api&app=gpodatapage&clientid=256&key=3e1a01bf63334cdb6bf3b583a8464839&resource=getcategorydata&category=number_of_privately_owned_firearms&location_id=194&format=raw"

## STATIC DATA 1
https://blog.mapbox.com/visualizing-gun-violence-in-america-bb36021b3aae
Image
0_a_4llBIWbEeO9ML5.png
https://www.thetrace.org/features/gun-violence-interactive-shootings-map/

## STATIC DATA 2
how-mass-shooters-got-their-guns-1443842838386-superJumbo-v11.png
https://www.nytimes.com/2018/02/15/us/6-stories-and-charts-to-help-you-better-understand-gun-violence.html

## STATIC DATA 3
_107405368_gun_people_killed_v4_-3x640-nc.png
https://www.bbc.com/news/world-us-canada-41488081

## STATIC DATA 4
key-findings-infographics.png
https://www.mhanational.org/issues/state-mental-health-america

## LINKS for web scraping
var url = 'https://newsapi.org/v2/everything?' +
'q=gun AND violence&' +
'from=2019-08-30&' +
'language=en&' +
'sortBy=relevancy&' +
'apiKey=75f26c6d9c014691bb58eb5f40530378';
var req = new Request(url);
fetch(req)
.then(function(response) {
console.log(response.json());
})